## 2019 Iranian FF POSM Spec
2019 Iranian FF - POSM ( Jan 22, 2019) |  |  | updated Jan 22, 2019
in GSC PKL & MV only, June 27 - July 3, 2019 ( 1 week) | [5 empty] | Deadline
1 | First draft of master visual (2 months prior) |  |  | 2 mths | Email softcopy for GSC approval | 2019-04-15
Adaptation design to collaterals listed below
2 | FF Button Badges/ticket design | Diameter 55 mm | Artwork | 230 |  | 2019-04-22
| Production button badges |  |  |  | Leadtime 1 week production leadtime | 2019-04-22
3 | Generic Bunting (2 per location) | 3' (w) x 6' (H) | 2 x 6 = 12 | 1mth | Deliver to participating cinemas | 2019-04-22
4 | Showtime Bunting (2/location) | 4' (w) x 6' (H) | 2 x 6 = 12 | 1mth | Deliver to participating cinemas | 2019-04-22
5 | Comp Passes | to calculate separately based on hall |  | 20% of total capacity |  | n/a
6 | Giant Banner - Pavilion KL | 8ft (w) X 18ft (H)
7 | Lightbox Poster | 27" (w) x 39" (H) |  | 4 | Deliver to GSC PKL to install (if launch in PKL | 2019-04-22
8 | Poster | 27" (w) x 39" (H) |  | 5 days prior | Deliver to PKL, MV | 2019-04-22
9 | GSC Monthly Emailer | 1000 px (W) x 1000 px (H) & 690 px (w) x 380 (h) | Jpeg | 1 | Email softcopy to GSC (Mac 2019 emailer) | 2019-04-22
| Film Fest movie info | Size : 984 pixel (W) x 1482 pixel (H) | jpeg |  |  | 2019-04-22
10 | Invitation Cards - KL |  |  | 20 | Deliver to GSC HQ | if applicable
11 | GSC Widget Oct 12 -28 | 282 x 160 pixels | jpeg | 1 | Email softcopy to GSC | 2017-09-16
12 | Flyers/Booklets tbc | to be confirmed by Embassy |  | 1000 | Deliver to cinemas 2 weeks prior | 2019-05-24
13 | GSC E-Poster | 1,280 (H) pixels x 768 (w) pixels | Jpeg - Applies to cinema with plasma tv | 3 | Email softcopy to GSC,(insertion June 13 - Jul 3) | Book April 2019
|  | File size: < 2mb |  |  |  | 2019-05-24
14 | GSC Mobile ROS Banner | 800 (w) x 125 (h) pixels | Jpeg | 1 | Email GSC (insertion June 13 - Jul 3) | Book April 2019
|  | File size: < 50kb |  |  |  | 2019-05-24
15 | Promo Banner (website) | • Size – 1920 pixels (w) x 450 pixels (h) Content safe area – 1170 (w) x 450 (h) • Format – JPEG • File Size – Less than 150KB • Please leave space for call-to-action button on bottom right side or the visual will be blocked. | Jpeg | 1 | Email softcopy to GSC ( insertion July 13 - Jul 3) | Book April 2019
2019-05-24
16 | Campaign Masthead (website) | • Size – 1920 pixels (w) x 600 pixels (h). Content safe area – 1170 (w) x 600 (h) • Format – JPEG • File Size – Less than 150KB | Jpeg | 1 | Email softcopy to GSC (insertion July 13 - Jul 3) | 2019-05-24
17 | GSC Video Wall Trailer | less than 1 min 30 secs File Size: < 40mb, below 100mb | Preferred Mpeg 4 & AVI. Other format Mpeg 1, 2, 3, DAT, WMV, M2V, VOB, MOV (Quick Time), RM (Real media) | 1 | 1 CD - Applies to GSC MV video wall n/a ; Submit first draft by May 24 *FF to povide the CD, Send to GSC Pavilion KL by 14 wrkg days before launch for cinema to test (NOT APPLICABLE NOW) | 2019-05-24
18 | GSC Widget -Star/Kosmo/MM/ | Specs : 1000 px (W) x 1000 px (H) | jpeg |  |  | 2019-05-24
19 | GSC In-Box Announcement | Size : | 1920 (w) x 600 (h) |  |  | 2019-05-24
20 | e-backdrop for hall screen |  | Size 1024 x 768 pixel refer to tab
21 | e-trailer |  | Preferred Mpeg 4 & AVI. Other format Mpeg 1, 2, 3, DAT, WMV, M2V, VOB, MOV (Quick Time), RM (Real media) | 1 | Send dropbox link to GSC
* subject to space availability
| POSM | With Sponsors logo | Only GSC, GSC Int Screens,
FF Logo
| Giant Banner | √
| Poster | √
| Lightbox poster | √
| Generic Buntings | √
| Showtime Buntings | √
| Flyers / Booklets | √
| Complimentary Passes | √
| Invitation Cards | √
| E-poster |  | √
| GSC Widget |  | √
| Mobile App (ROS Banner) |  | √
| Super Banner |  | √
| Promo Banner (website) |  | √
| Campaign Masthead (website) |  | √
| Video Wall |  | √
| E-mailer |  | √

## POSM Allocation
2019 Iranian FF - POSM Allocation (Recommended allocation only)
No | Item | Size | Total Qty | Allocation
|  |  |  | GSC MV | GSC 1 U | GSC PKL | GSC NUS | GSC GPP | GSC SKK | GSC C1K | GSC Paradigm JB
1 | Giant Banner - Pavilion KL | 8ft (w) X 18ft (H) | 0 | - | - | 0 | - | - | - | - | 0
2 | Lightbox Poster | 27" (w) x 39" (H) | 4 | 0 | - | 4 | - | 0 | - | 0 | 0
3 | Poster | 27" (w) x 39" (H) | 1 | 0 | 0 | 1 | - | 0 | 0 | 0 | 0
4 | Generic Bunting | 3' (w) x 6' (H) | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
5 | Showtime Bunting | 4' (w) x 6' (H) | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
6 | Flyers/Booklets (500) | 2\ | 1000 | 500 | 0 | 500 | 0 | 0 | 0 | 0 | 0
Person in Charge:
No | Location | PIC |  | Address |  |  | Contact Number |  | e-mail
1 | GSC Mid Valley | Mr. Lee Kong Yew/ Manager on Duty |  | Lot T-001, Level 4, Mid Valley Megamall Shopping Complex, Batu 2 1/2, Jalan Klang Lama, 5800 Kuala Lumpur |  |  | 03-2938 3113/ 017-263 3550 |  | gscmv@gsc.com.my
2 | GSC 1 Utama | Mr Puspanathan/ Manager on Duty |  | Lot E403, 4th Floor, 1 Utama Shopping Centre, No. 1, Lebuh Bandar Utama, Bandara Utama Damansara, 47800, Petaling Jaya |  |  | 03- 7722 2440/ 019-221 7765 |  | gsc1u@gsc.com.my
3 | GSC Pavilion KL | Mr. Mohammad Hadi/ Manager on Duty |  | Lot C5.02 Level 5 & Lot C6.01 Level 6, Pavilion KL. No 168, Jalan Bukit Bintang, 55100, KL |  |  | 03-2142 1463/ 017- 666 5116 |  | gscpkl@gsc.com.my
4 | GSC NU Sentral (TBC) | Mr. Thanaraj / Manager on Duty |  | Lot L5.14, Level 5 NU Sentral , No 201 Jalan Tun Sambanthan 50470, Kuala Lumpur |  |  | 03-2260 1157/013-689 1051 |  | gscnus@gsc.com.my
5 | GSC Gurney Plaza | Mr. V. Kaviaarasa/ Manager on Duty |  | Lot 170-07-01, Plaza Gurney, Persiaran Gurney, 10250 Penang |  |  | 04-228 2201/ 012-516 7582 |  | gscgurney@gsc.com.my
6 | GSC Suria Sabah Mall | Mr. James Aman Jr / Manager on Duty |  | 8th Floor, Suria Sabah Shopping Mall, Jalan Tun Fuad Stephen 88000 Kota Kinabalu |  |  | 088 - 486 638 / 016 - 586 0228 |  | gscc1k@gsc.com.my
7 | GSC CityONE Megamall | Mr. Nuresmandy / Manager on Duty |  | Lot No.MT12, 3rd Floor, CityONE Megamall, No.1, Jalan Song 93350 Kuching |  |  | 082 - 532 948 / 019 - 898 0606
gscc1i@gsc.gsm.my
8 | GSC Paradigm JB | Mr Mohd Fizri |  | 7F-01 & 7F-02, Paradigm Mall Johor Bahru, |  |  | 07 - 244 8005/244 7775/
|  |  |  | Jalan Skudai, |  |  | 019-7854256 |  | gscpjb@gsc.com.my
81200 Johor Bahru

## Button Badges
Button Badges Info - design by main organiser, production cost by GSC
can also use this design & dimensions for the Film Festival launch stickers for invited guests
1) Sample
IMPORTANT: Please include "Golden Screen Cinemas Sdn Bhd (3609-M)", GSC website and film festival website (if any) in the button as shown in the picture.
Font is "Arial".
2) Size
5.5cm (w) x 5.5cm (h)
No. | Location | Total (pcs)
1 | GSC Pavilion KL | 120 | 120
2 | GSC 1 Utama | 0 | 70
3 | GSC Mid Valley | 110 | 110
4 | GSC NU Sentral | 0 | 70
5 | GSC Gurney Plaza | 0 | 70
6 | GSC Suria Sabah,Kota Kinabalu | 0 | 60
7 | GSC CityOne Megamall,Kuching | 0 | 60
8 | GSC Paradigm JB | 0 | 90
| Total | 230 | rounded up

## Widget (Star,Kosmo, CP, MM)
7, 2018WIDGET IN THE STAR ONLINE, CHINA PRESS, KOSMO, MALAYSIA updated April 16, 2018
1) Widget - in The Star Online ( News & Star 2 section) www.thestar.com.my
value RM2015,982 per week | Star Online |  | Kosmo Online ww.kosmo.com.my
Unique visitors : 1,748,000
Specs : 1000 (H) x1000(H), less than 100 kb as at Aug 9,2018 (old dimension was 690 px (W) x 380 px (H))
2) Widget - Kosmo Online www.kosmo.com.my
2014 info : unique visitors : 2.9 million, page views: 12.8 million
Specs : 1000 (H) x1000(H), less than 100 kb as at Aug 9,2018 (old dimension was 690 px (W) x 380 px (H))
value RM5,538 per week
3) Widget - China Press Online www.chinapress.com.y
Unique visitors : 1,1513
value RM3,461 per week
Specs : 1000 (H) x1000(H), less than 100 kb as at Aug 9,2018 (old dimension was 690 px (W) x 380 px (H))
100% SOV |  | China Press Online www.chinapress.com.my
Placement : Lifestyle & Ebtertaiment and all subsequent pages
4) Widget - Malay Mail Online www.themalaymailonline.com.my
Desktop pageviews - 11,753,718, unique visitors - 3,647,962
Mobile pageviews - 5,783,535, unique visitors - 2,695,538
value RM8,000 per week
Specs : 1000 (H) x1000(H), less than 100 kb as at Aug 9,2018 (old dimension was 690 px (W) x 380 px (H))

## complimentary pass
NOT applicable for FOC Film Festival
Complimentary pass - where applicable ( Not applicable for FF whereby tickets are given out for free)

## poster,eposter & lgtbox poster
Poster | e-poster | lightbox poster (printing front & back) 1 sheeter
size : 27" (w) x 39" (H) | Size : 1,280 (H) pixels x 768 (w) pixels | size : 27" (w) x 39" (H)
| File size: < 2mb | Material - duratrans/ backlit tranparency
for GSC MV & PJB videowall - 1920 x 1080 pixels
for Fb promo - 1000 (w) x 1000(h)

## Generic & Showtime bunting
Generic Bunting | Showtime Bunting
size: 3' (w) x 6' (H) | Size : 4' (w) x 6' (H)

## Promo Banner
Promo Banner (GSC Website)
• Size – 1920 pixels (width) x 450 pixels (height) Content safe area – 1170 (w) x 450 (h) • Format – JPEG • File Size – Less than 150KB • Please leave space for call-to-action button on bottom right side or the visual will be blocked.
Back up promotion banner ( in case wht's hot banner is fully allocated
1920 x 690 pixels

## Campaign Masthead
Campaign Masthead ( GSC website)
to use movie stills for masthead, visual to be different from GSC website
promo banner
• Size – 1920 pixels (width) x 600 pixels (height). Content safe area – 1170 (w) x 600 (h) • Format – JPEG • File Size – Less than 150KB

## GSC website movie info
GSC website movie info page keyart
Use movie stills
Size : 984 pixel (W) x 1482 pixel (H)
12.5cm (w) x 18.8 cm (H)
http://www.ceskatelevize.cz/porady/10745118963-hlas-pro-rimskeho-krale/21551212101/

## GSC backdrop frame
GSC backdrop frame
Size : | 7.5 ft x 7.5 ft

## ROS Banner (Mobile)
ROS Banner - GSC Mobile app
2 SIZE : 800 (w) x 125 (h) pixels
File size: < 50kb , jpeg

## GSC Generic monthly e-mailer
e-mailer /website thumbnail - monthly, disseminated first week of the month
size :1000 px x 1000 px & Option 1: 690 px (w) x 380 px (h)
and Option 2: 628(w) x 375 (h)

## GSC In-Box mobile app
GSC In-box (Mobile app - Announcement)
Size : | 1920 (w) x 600 (h) | for example
same as GSC websie masthead size
Title of event/promtion: |  | 2018 Japanese Film Festival
Description of event /Promotion ( 2000 characters): |  | 2018 Japanese Film Festival will be screened from August 23 - 29, 2018. Ticket can be purchased @RM10 each from Aug 21 onwards
in the following locations - GSC Pavilion KL, GSC Mid Valley Megamall, GSC 1Utama, GSC NU Sentral, GSC Gurney Plaza Penang and GSC Paradigm JB.
Booking Date: |  | Aug 9 - 29, 2018

## GSC e-backdrop
GSC e-backrop on cinema screens
to be projected onto the cinema screens
during press conference and launch
Embassy /organiser to bring own lapop/hdmi cables etc
and assign own personnel to project this from projector room
Please give two (2) options
a) Size 1024 x 768 pixel
b) Size 1998 x 1080 pixel
to ensure there is space/border around (see visual) as
GSC screens may differ in size in the different halls.
Need to adjust

## GSC MV video wall
GSC videowall poster
specs requirement:
a) GSC MV 2816 x 928 HD
b) GSC PJB 1680 (W) x 960(H) HD

## Daily Express KK cinema listing
Daily Express , KK cinema listings (only applicable for Film festival in GSC SKK)
Size required : Banner
size - 3 column x 3 cm ( 1 column is 3.3cm )
or 9.9 cm x 3 cm size