## Check List
2019 IRANIAN FILM FESTIVAL GENERAL CHECKLIST updated Jan 22, 2019
Festival Name: 2019 Iranian Film Festival
Festival Date: June 27 - July 3, 2019 ( 1 week)
Locations : exclusively in GSC PKL.
NO | ITEM | ACTION |  | DEADLINE | REMARKS | DONE
|  | GSC | FF
GENERAL
1 | Draft Iranian FF Proposal | √ |  | 2019-05-24 | Prepared by GSC.
2 | IFF Agreement (draft) | √ | √ | 2019-05-24 | Prepared by GSC, Embassy to amend. Total 2 copies. Both parties to sign & keep a copy each GSC/Embassy
FILMS
1 | Selection of Films |  | √ | 27/3/2019(3months) | Selection by Embassy
2 | Issue Letter to Censorship Board |  | √ | 2019-03-27 | Embassy to inform of the festival, request speedy censorship & blocking/cuts.
3 | Censorship of Films |  | √ | 2019-03-27 | Embassy to submit DCPs/blu-ray films for initial censorship.
4 | Final List of Films |  | √ | 2019-04-24 | Embassy to inform GSC
5 | Film Publicity Materials |  | √ | 2019-04-29 | Initial design by Embassy. Refer to POSM list
6 | Preferred Programming Schedule |  | √ | 2019-04-29 | GSC Programming drafts, based on limited screenings, brief from Embassy
7 | Approval by Embassy | √ |  | 2019-05-03 | Work out screening schedule & advise Naza on schedule with timings & no. of screenings for each film.
8 | Changes for FF schedule , if any |  | √ | n/a | to finalise
9 | Image Stills and Poster File of Films |  | √ | 2019-04-24 | Embassy to provide poster files, movie info to GSC
10 | GSC to provide server type model to Embassy (DCPs) | N/A |  | 2019-04-29 | GSC Technical will provide server type model for DCPs (where applicable)
11 | Programming - Film code | √ |  | 2019-05-13 | Send full film list with censorship ratings to GSC Programming - GSC cinemas.
p | Delivery of DCPs or blu-ray for PC/opening / general screening |  | √ | 2019-05-27 | Embassy to deliver DCPs (PKL first) to cinemas, kdms and arrange for pick-up one day after the end of Film Festival.
17 | Ingest, Testing of dcp/kdms in cinemas (DCP, where applicable) |  | √ | May 27 - June 3 | GSC PKL
18 | Delivery & Blu-Ray testing in all location (where applicable) | √ | √ | 2019-05-27 | n/a
19 | Cinema to check the DCP (ie English Subtitle) and update HQ | √ |  | May 27 - June 3 | After ingestion, cinema need to check the DCPs esp English subtitles to ensure everything is in good condition, and inform HQ about the DCPs status
20 | Films selection/manual blocking info from Embassy |  | √ | 7 wkg days prior (June 17) | Embassy to share details of personnel for manual blocking and issue letter of authorisation with name, I.C. No, tel nos
All materials to carry GSC & Int'l Screens logo as official venue.
PUBLICITY MATERIALS
1 | First draft of master visual |  | √ | 2019-04-26 | Embassy to design, send to GSC for approval, then Embassy to print.
5 | Complimentary Passes (Qtn TBC) |  | √ | not applicable | Embassy to design, send to GSC for approval, then Embassy to print.
6 | Posters (Qtn : 6) |  | √ | 2019-05-10 | Embassy to design, send to GSC for approval, then Embassy to print.
7 | Giant Banner (Qtn : 1) |  | √ | 2017-04-13 | Embassy to design, send to GSC for approval, then Embassy to print.
8 | Lightbox Poster 1U |  | √ | 2019-05-10 | Embassy to design, send to GSC for approval, then Embassy to print.
9 | Leaflet/Booklet (movie synopsis & showtimes) |  | √ | 2019-05-10 | Embassy to design, send to GSC for approval, then Embassy to print.
10 | e-Invitation |  | √ | 2019-05-10 | Embassy to design, send to GSC for approval
11 | e-Poster / e plasma |  | √ | 2019-05-10 | Embassy to design and send to GSC to be featured on e-poster panels.
12 | e-Mailer |  | √ | 2019-05-10 | Embassy to design and send to GSC to be featured in GSC _April e-mailer.
| movie info for GSC website |  | √ | 2019-04-26 | Embassy to give updated info with visuals (refer to collateral specs
13 | What's Hot Banner (GSC website) |  | √ | 2019-05-10 | Embassy to design and send to GSC to be upload in GSC website
14 | Campaign Masthead (GSC Website) |  | √ | 2019-05-10 | Embassy to design and send to GSC to be upload in GSC website
15 | ROS banner (mobile app) |  | √ | 2019-05-10 | Embassy to send to GSC to be featured in GSC mobile app (iOS & Android).
16 | GSC Widget |  | √ | 2019-05-10 | Embassy to design and send to GSC to be featured on Star 2 Online.
17 | Video wall |  | √ | 2019-05-20 | Designed by Embassy Production House and sent to GSC for approval & play at video wall GSC PKL
18 | e-trailer |  | √ | 2019-05-20 | Designed by Production House and sent to GSC for approval & insert into e-trailer by CineAd
19 | "Blocking of Cuts" Notice |  | √ | 2019-06-13 | draft by GSC HQ, email to the cinemas
PROMOTION
1 | GSC Monthly Mailer | √ |  | Book April, materials April | Provide festival info & disseminate to Digital Marketing
2 | Website (www.gsc.com.my) | √ |  | 2019-05-15 | Provide festival info, movie synopsis and screening schedule
3 | Media partners (Promo Partner) | √ | √ | 2019-05-15 | Embassy to approach media for tie-ups.
4 | GSC e-plasma screens @ Cinemas | √ |  | 2019-05-15 | Provide festival info to CineAd.
5 | GSC mobile app | √ |  | 2019-05-15 | book and Provide visuals to CineAd.
6 | Newspaper Cutting | √ |  | During FF | To compile daily for records and work out total value.
Press conference - june 18 , GSC MV Hall 10
1 | Hall Booking GSC MV Hall 10(FOC) | √ |  | 2019-05-17 | Book GSC MV Hall 10 ( S &P)
2 | Programme for the day |  | √ | 2019-05-15 | to be confirmed by Embassy
3 | Media & Guest invitation |  | √ | 2019-05-15 | Embassy
4 | Ensure film availability for Press conference DCP/kdm/blu-ray | √ | √ | 2019-05-15 | attach GSC Intl Screen & GSC leader, classifciation leaders to film
5 | Hall seat chart for CZFF | √ |  | During FF | GSC to email hall seating chart to Embassy
6 | Emcee for PC event |  | √ | 2019-05-13 | Embassy to identify
7 | Press release draft |  | √ | 2019-05-13 | Embassy to share with GSC
8 | Adminscript | √ | √ | 2019-05-17 | GSC to draft and share with Embassy
9 | Identify resources-manpower | √ | √ | 2019-05-15 | reception, photographer, PA system, bunting, rostrum
10 | Press kit -release, Movie info, movie schedule |  | √ | 2019-05-15 | Embassy share with GSC
11 | Arrival of VIP/Ambassador | √ | √ | june 18, during PC | Embassy to advise GSC
12 | guest registration |  | √ | June 18, during PC | Embassy to identify guests on location
FF launch in KL - (June 26) @ GSC PKL Hall 3@7pm
1 | Hall Booking (PKL Hall 3) | √ |  | 2019-05-02 | S & P Book hall 3 with AE & THX foyer for catering. | done
2 | Hall Booking Quotation | √ |  | 2019-05-02 | Embassy to sign off hall booking quotation and revert to keith(S&P) to issue tax invoice
3 | Programme of the Launch (1 month) |  | √ | 2019-05-22 | To be confirmed by Embassy
4 | Ensure Availability of Film ( 2 wks) |  | √ | 2019-05-27 | Attach International Screens & Classification leaders to the film.
5 | Hall Seating Plan to FF (2 wks) | √ |  | 2019-05-27 | GSC to sent hall seating plan to Embassy
6 | Guests Invitation (2 wks) | √ | √ | 2019-05-27 | GSC to share GSC reps for launch event
7 | Speech for GSC (2 wks) | √ |  | 2019-05-27 | GSC to draft speech for GSC representative at the launch.
8 | Catering (1 month) |  | √ | 2019-05-27 | Embassy to Set up meeting with caterer & S&P
9 | Emcee (2 wks) |  | √ | 2019-05-27 | Embassy to identify emcee for the opening launch
10 | Admin Script (2 wks) | √ |  | 2019-05-27 | Initial draft /Embassy
11 | Arrival of Ambassador |  | √ | tbc | Embassy to advise GSC arrival of Ambassador. Representative of GSC to greet the Ambassador at the entrance of the cinema.
12 | Identify Helpers ( 1 wk) | √ |  | 2019-05-27 | 2 x Reception, 1 x Photographer, 1 x On-Ground, 1 x Usher VIP to the stage for speech.
13 | Reserve 2 Tables in Gold Class ( 1 wk) | √ |  | tbc | For Ambassador/VIPS.
14 | Reserve 2 Rows of Seat in the Hall ( 1 wk) | √ |  | tbc | 1st row from the screen for VIP for speech & 1 middle row for VIP to watch the film.
15 | draft press release - launch event (event day) | √ |  | tbc | GSC
16 | Guests Registration (event day) | √ | √ | event day | Embassy/Main Organisers
OTHERS
1 | Email Cinemas (Marketing brief, schedule, etc) | √ |  | 2019-06-13 | Email cinemas about festival, ticket pricing, launch , etc
2 | Report | √ |  | 2019-07-31 | Prepared by GSC
3 | Daily admission report |  |  | June 27 - July 3
Censorship board contact :
For movie censorship, you can contact Mr Yew Kong (yewkong@megafilem.com) or reach him at 03 9222 1192 / 93/95.
Formulas:
DEADLINE = [DEADLINE, row above]